## Oct
PLANNING PHASE
OCTOBER 2011
Sunday | Monday |  | Tuesday | Wednesday | Thursday | Friday | Saturday
2011-10-01
2011-10-02 | 2011-10-03 |  | 2011-10-04 | 2011-10-05 | 2011-10-06 | 2011-10-07 | 2011-10-08 | Yom Kippur
2011-10-09 | 2011-10-10 | Columbus Day | 2011-10-11 | 2011-10-12 | 2011-10-13 | 2011-10-14 | 2011-10-15
EOY Kick-Off
Program overview
and EOY trends
12pm EST
2011-10-16 | 2011-10-17 |  | 2011-10-18 | 2011-10-19 | 2011-10-20 | 2011-10-21 | 2011-10-22
EOY Service Module
Call #2
Hours - 12pm EST
Focus: Campaign
Theme Brainstorm
2011-10-23 | 2011-10-24 | United Nations Day | 2011-10-25 | 2011-10-26 | 2011-10-27 | 2011-10-28 | 2011-10-29
2011-10-30 | 2011-10-31 | Halloween |  |  |  | Notes:
[6 empty] | www.vertex42.com |  | © 2009 Vertex42 LLC

## Nov
BUILDING PHASE
NOVEMBER 2011
Sunday |  | Monday | Tuesday | Wednesday | Thursday |  | Friday |  | Saturday
|  |  | 2011-11-01 | 2011-11-02 | 2011-11-03 |  | 2011-11-04 |  | 2011-11-05
EOY Service Module
Call #3
Hours - 12pm EST
Focus: Writing for
the web
2011-11-06 | Daylight Savings | 2011-11-07 | 2011-11-08 | 2011-11-09 | 2011-11-10 |  | 2011-11-11 | Veterans Day | 2011-11-12
|  |  |  | EOY Service Module |  |  | Finish Planning
|  |  |  | Call #4 |  |  | Your EOY Campaign
|  |  |  | Hours - 12pm EST |  |  | Using Guide
Focus: Campaign
Walk Through and Q&A
2011-11-13 |  | 2011-11-14 | 2011-11-15 | 2011-11-16 | 2011-11-17 |  | 2011-11-18 |  | 2011-11-19
Start building your
EOY campaign
|  | Production | Production | Production | Production |  | Production
2011-11-20 |  | 2011-11-21 | 2011-11-22 | 2011-11-23 | 2011-11-24 | Thanksgiving | 2011-11-25 |  | 2011-11-26
|  | Production | Production | Production
2011-11-27 |  | 2011-11-28 | 2011-11-29 | 2011-11-30
You should finish
your campaign, do
QA and testing this
week at the latest
|  | Production | Production | QA
Notes:
[7 empty] | www.vertex42.com |  |  | © 2009 Vertex42 LLC

## Dec
EXECUTING PHASE
DECEMBER 2011
Sunday |  | Monday |  | Tuesday | Wednesday |  | Thursday |  | Friday | Saturday
|  | 1900-01-27 |  | 1900-01-28 | 1900-01-29 |  | 2011-12-01 |  | 2011-12-02 | 2011-12-03
You should finish
your campaign, do
QA and testing this
week at the latest
|  | Production |  | Production | QA |  | QA |  | QA
2011-12-04 |  | 2011-12-05 |  | 2011-12-06 | 2011-12-07 |  | 2011-12-08 |  | 2011-12-09 | 2011-12-10
|  | Schedule all your |  |  | EOY Service Module
|  | EOY appeal messages |  |  | Call #5
Hours - 12pm EST
Focus: Scheduling
the Campaign
2011-12-11 |  | 2011-12-12 |  | 2011-12-13 | 2011-12-14 |  | 2011-12-15 |  | 2011-12-16 | 2011-12-17
First appeal message
launches this week
2011-12-18 |  | 2011-12-19 |  | 2011-12-20 | 2011-12-21 | Chanukkah | 2011-12-22 | Dec. Solstice | 2011-12-23 | 2011-12-24 | Christmas Eve
Second appeal message
launches this week
2011-12-25 | Christmas Day | 2011-12-26 | Kwanzaa begins | 2011-12-27 | 2011-12-28 |  | 2011-12-29 |  | 2011-12-30 | 2011-12-31 | New Year's Eve
Final appeal message
launches this week
Notes:
[9 empty] | www.vertex42.com |  | © 2009 Vertex42 LLC

## Jan2012
REPORTING PHASE
JANUARY 2012
Sunday |  | Monday |  | Tuesday | Wednesday | Thursday | Friday | Saturday
2012-01-01 | New Year's Day | 2012-01-02 |  | 2012-01-03 | 2012-01-04 | 2012-01-05 | 2012-01-06 | 2012-01-07
2012-01-08 |  | 2012-01-09 |  | 2012-01-10 | 2012-01-11 | 2012-01-12 | 2012-01-13 | 2012-01-14
EOY Service Module
Call #6
Hours - 12pm EST
Focus: Reporting
|  | Analytics Processing |  | Analytics Processing | walk-through | Analytics Processing | Analytics Processing
2012-01-15 |  | 2012-01-16 | ML King Day | 2012-01-17 | 2012-01-18 | 2012-01-19 | 2012-01-20 | 2012-01-21
|  | Analytics Processing |  | Analytics Processing | Analytics Processing | Analytics Processing | Analytics Processing
2012-01-22 |  | 2012-01-23 |  | 2012-01-24 | 2012-01-25 | 2012-01-26 | 2012-01-27 | 2012-01-28
EOY Service Module
Final Call
12pm EST
Focus: Benchmarking
Statistics Review
2012-01-29 |  | 2012-01-30 |  | 2012-01-31
Notes:
[7 empty] | www.vertex42.com |  | © 2009 Vertex42 LLC